## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8
| 03/12/2025 - 03/19/2025 | 03/19/2025 - 03/26/2025 | 03/26/2025 - 04/02/2025 | 04/02/2025 - 04/09/2025 | 04/09/2025 - 04/16/2025 | 04/16/2025 - 04/23/2025 | 04/23/2025 - 04/30/2025 | 04/30/2025 - 05/07/2025
Manish
What tasks did I work on / complete? | understanding the project's requirements, Creating class diagrams, understarding databases | Devloped UI wireframes for Login page and Home Page | View Details including reviews and ratings for each restaurant | Logging as RestaurantManger, viewing istings owned by this owner | Check for duplicate listings for the Admin | Finished admin part | Added images to the restaurents - can add and update them along with description | website bug fixes and updated Customer interface
What am I planning to work on next? | create the basic framework | developing functionalities for Customer | Connecting view details with frontend | Working on integrating it with frontend | Remove entries (when businesses close down) for the admin | Should work on adding images to the restaurents | bug fixes and minor UI changes | NA
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #7
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: we discussed our task progress in the daily meeting and solved any blockers we faced together (XP value: feedback and Simplicity)
Venkat | bar: Week #2 to Week #4
What tasks did I work on / complete? | Determining entities,attributes along with the relationship | Register functionality for all 3 roles | Creating wireframe for Admin | Understanding map Apis | Integrated map Api in the backend | Finished integrating with map API | Integrated everything for Customer role - both front end and backend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | Table creation and DB design,mock data for all tables | Login functionality for all 3 roles | Search for restaurents using name, type of cusines | Integrating map Api | Should work on the frontend for searching restaurents using location | Need to work on integrating everything done till now | AWS deployment | NA
What tasks are blocked waiting on another team member? | NA | Creating wireframe for Admin | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Through regular meetings, everyone discussed functionalities in details which help us achieved the well reviewed solution.; Week #7: Communication with the team related to AWS deployment
Tareesh | bar: Week #2 to Week #4
What tasks did I work on / complete? | Architecture diagram ,Project setup & boilerplate code | Building the database structure for the Restaurents, Customers, Restaurants, Reviews, Roles, and Search Data | Integrating frontend and backend and testing for bugs till now | Update name, address, contact info, Hours fo RestaurantManger | Sorted frontend ui debugging issues | Finished map Api frontend | Integrated everything for admin both frontend and backend | Developed backend implementation for the system to prevent conflicting assignments,minor bug fixes and testing the complete flow of the application
What am I planning to work on next? | DB design | Created UI wireframe for login and RestaurantManger | Add a new listing for RestaurantManger | Integrating it with front end | Working on the frontend of the map api | Working on AWS deployment | Created wireframworks for remaining screens | NA
What tasks are blocked waiting on another team member? | bar: Week #1 to Week #8
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Communication - Discussion about technology stack and requirements | Communication - Discussed about the design decisions with the team and got it reviewed. | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication with the team related to any other screens. | Communication with the team related to approach and integrations
Mohan
What tasks did I work on / complete? | UI wireframe for login page and Home page | Integrated Mongodb , sign in page mock. | Created customer entities and relationships | Integrated login and signup page on frontend | Understanding concepts of AWS for deployment | Analytics dash board for admin. Merge backend and frontend for admin | updated UI for Customer | Minor bug fixes, hosting the application on aws
What am I planning to work on next? | Integrate Mongodb & mock login page | Designing UI | Creating admin and Customer page frontend | Testing all the features done till now | Front end UI for Customer, RestaurantManger | Working on Aws | Fix issues in selecting restaurents usinf cuisines | NA
What tasks are blocked waiting on another team member? | NA | None | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Communication - others choice of design